## Ref Sheet
USER STORIES
SHORT/SIMPLEDSCRPTION OF THE FEATURE/RQMNT TOLD FROM THE PERSPECTIVE OF A USER
As a <TYPE OF USER>, I want <SOME GOAL>, so that <SOME REASON>
As a e-bankng customer, I shll be able to make fund transfer online, so that I need not to walkinto the branch for every transaction that need to make
EPIC
Larger USER Stories
THEME
related user stories grouped together
Story Point
Unit of measure of effortrequired to complete a particular task
|  |  | user story --> 1 or more task | 1:N
|  |  | epic --> user stories | 1:N
user story can be stand alone
Acceptance criteria
Chklst to determine if ll the parameterof the rqmnt is compete
PO can validate the assumptions that team
QA wuld comeup with test cases against the acceptanc criteria
Theme
Epic
User stories
User stories
Tasks
Acceptance critria

## Theme & Epic
THEME
TH1 | As an bank account customer, shall have the option for online banking, for ease of banking
EPIC
EP1 | As a user shall have the option to register
EP2 | As a User shall have the option to login
EP3 | As a User shall have the option to do funds transfer
EP4 | As a User shall have the options to pay bills online
Assignment
1 | User stories tab | come up with US for Epic 2 & 4
2 | Product Backlog tab | Come up with tasks,priority,acceptance criteria,storypoint for the userstoris from step 1
3 | Sprint 2 tab | select a few US fo sprint 2. Take into consderation the sum of story points & the priority
4 | Velocity Graph tab | Draw velocity chart
5 | Burndown Chart tab | Draw Burndown Chart

## User Stories
ID | User Story Descriptions | EPIC | Status
US1 | As a first time user, shall have the option to register on the homepage | EP1 | Completed
US2 | As a first time user, shall have the option to enter the account details and personal details in the registration page | EP1 | Completed
US3 | Aa a first time user, shall have the option to choose user Id and PW | EP1
US4 | As a first time user, shall have the option to confirm my details | EP1
US5 | Aa a first time user, shall have the option to get a confirmation text/email | EP1
U6 | As a registered user, shall have the login option on the homepage | EP2 | Completed
U7 | As a registered user, shall have the option to login using the User ID and PW | EP2 | Completed
U8 | As a registered user, shall have the option to see the account summary on the landing page | EP2 | Completed
U9 | As a registered user, I shall have the option to have detailed summary for each account so that I view the summary details. | EP2 | Completed
U10 | As a registered user, shall have the option for funds transfer on the landing page | EP3 | Completed
U11 | As a registered user, shall have the option add recipient | EP3 | Not Started
U12 | As a registered user, shall have the option to send funds between my accounts | EP3 | Not Started
EP2 - Review th existing; add if you wish to
Ep4 - Come up with your own US

## Product Backlog
ID: | Task | Priority | Acceptance Criteria | Status | Story Points
EP1_US1_T1 | The homepage shall have the register option on the right side of the screen | 1 | The register option shall be a rectangular box on the right of the screen and shall take to the registration page when selected | Completed | 3
EP1_US2_T1 | The user shall be provided data input boxes for account and personal information in the registration page | 2 | The Account number data input box shall be a numeric data input box with max length of 12 and personal details shall be data input box for name, address and phone number | Completed | 2 | The Account number data input box shall be a numeric data input box with max length of 12. There should be a text box to enter the Name. Ther should be Numeric box to enter the phone number of the recipient There should be 3 text boxed one for each address line.
EP1_US3_T1 | The log in ID shall be data input box | 1 | The data input box shall accept alphanumeric characters with a max length of 15 | Committed | 5
EP1_US3_T2 | Below the login ID shall be the password data input box | 3 | The paswword data input box shall accept alphanemric and special characters with a max length of 10 | Completed | 2
EP1_US4_T1 | The user shall have the option to confirm the details beside password box | 1 | The confirm details option shall notify the user if details not filled | Completed | 3 | Story Point | Priority
EP1_US5_T1 | The user shall be provided with a register button below the pw box | 1 | The register option shall be a rectangular selct box which shall check whether the User ID and PW entered are valid and shall if valid shall send a confirmation text/email to user | Completed | 3 | 1 = Least Effort | 1 = HIGH
EP1_US5_T2 | The user shall be displayed an error is data incorrect and shall be given an option to retype/re-enter details | 2 | If there is an error in the data entered by user for ID/PW or personal details, that particular data input box shall be cleared of data and show a red color border to help the user retype the info | Acceptaed | 4 | 2 = Low Effort | 2 = MEIDUM
[6 empty] | 3 = Medium Effort | 3 = LOW
EP2 & EP4 | As a registered user, I shall have the option to have detailed summary for each account so that I view the summary details. |  | Scenario: GIVEN WHEN THEN |  |  | 4 = High Effort
5 = Advanced Effort
Fibiocci series
1
2
3
5
8
|  | 1 | 5
|  | 1 | 5
|  | 1 | 4
|  | 1 | 5
|  | 1 | 4
|  | 1 | 3
|  | 1 | 3
|  | 2 | 3
|  | 2 | 2
|  | 2 | 5

## Sprint 1
ID: | User Story Descriptions / Task | Priority | Acceptance Criteria | Story Points | Assigned To | Est Time | Est End Date | Actual Time | Start Date | End Date: | Status
EP1_US1_T1 | The homepage shall have the register option on the right side of the screen | 1 | The register option shall be a rectangular box on the right of the screen and shall take to the registration page when selected | 3 | Joe | N/A | N/A | 180 | 2018-01-02 | 2018-01-04 | Completed
EP1_US3_T1 | The log in ID shall be data input box | 1 | The data input box shall accept alphanumeric characters with a max length of 15 | 5 | Joe | N/A | N/A | 60 | 2018-01-03 | 2018-01-04 | Completed
EP1_US4_T1 | The user shall have the option to confirm the details beside password box | 1 | The confirm details option shall notify the user if details not filled | 3 | Jack | N/A | N/A | 360 | 2018-01-05 | 2018-01-09 | Completed
EP1_US5_T1 | The user shall be provided with a register button below the pw box | 1 | The register option shall be a rectangular selct box which shall check whether the User ID and PW entered are valid and shall if valid shall send a confirmation text/email to user | 3 | Mira | N/A | N/A | 60 | 2018-01-03 | 2018-01-06 | Completed
EP1_US2_T1 | The user shall be provided data input boxes for account and personal information in the registration page | 2 | The Account number data input box shall be a numeric data input box with max length of 12 and personal details shall be data input box for name, address and phone number | 2 | Mira | N/A | N/A | 180 | 2018-01-04 | 2018-01-12 | Completed
EP1_US5_T2 | The user shall be displayed an error is data incorrect and shall be given an option to retype/re-enter details | 2 | If there is an error in the data entered by user for ID/PW or personal details, that particular data input box shall be cleared of data and show a red color border to help the user retype the info | 4 | Mira | N/A | N/A | 240 | 2018-01-07 | 2018-01-15 | Completed
[5 empty] | Joe | N/A | N/A | 240 | 2018-01-07 | 2018-01-15 | Completed

## Sprint 2
ID: | User Story Descriptions / Task | Priority | Acceptance Criteria | Story Points | Assigned To | Est Time | Est End Date | Actual Time | Start Date | End Date: | Status
[5 empty] | Joe | N/A | N/A | 180 | 2018-01-02 | 2018-01-04 | Completed
[5 empty] | Joe | N/A | N/A | 60 | 2018-01-03 | 2018-01-04 | Completed
[5 empty] | Jack | N/A | N/A | 360 | 2018-01-05 | 2018-01-09 | Completed
[5 empty] | Mira | N/A | N/A | 60 | 2018-01-03 | 2018-01-06 | Completed
[5 empty] | Mira | N/A | N/A | 180 | 2018-01-04 | 2018-01-12 | Completed
[5 empty] | Mira | N/A | N/A | 240 | 2018-01-07 | 2018-01-15 | Completed

## Velocity Graph
No of Sprints | Planned story points | Actual Story Points
1 | 20 | 22
2 | 20 | 18
3 | 20 | 21
4 | 20 | 21
5 | 20 | 22

## Burndown Chart
| Covered Story Points |  | Remaining Story Points
Days | Planned | Actual | Planned | Actual | Story points Covered
0 |  |  | 200 | 200
1 | 10 | 5 | 190 | 195 | 5
2 | 10 | 7 | 180 | 188 | 12
3 | 10 | 8 | 170 | 180 | 20
4 | 10 | 9 | 160 | 171 | 29
5 | 10 | 9 | 150 | 162 | 38
6 | 10 | 9 | 140 | 153 | 47
7 | 10 | 15 | 130 | 138 | 62
8 | 10 | 9 | 120 | 129 | 71
9 | 10 | 9 | 110 | 120 | 80
10 | 10 | 13 | 100 | 107 | 93
11 | 10 | 15 | 90 | 92 | 108
12 | 10 | 11 | 80 | 81 | 119
13 | 10 | 15 | 70 | 66 | 134
14 | 10 | 12 | 60 | 54 | 146
15 | 10 | 14 | 50 | 40 | 160
16 | 10 | 9 | 40 | 31 | 169
17 | 10 | 9 | 30 | 22 | 178
18 | 10 | 9 | 20 | 13 | 187
19 | 10 | 9 | 10 | 4 | 196
20 | 10 | 4 | 0 | 0 | 200